## Sheet1
meeting_id | date | project | decisions | risk_description | risk_impact | risk_owner | risk_status | issues | dependencies | action_task | action_owner | action_due_date | change_requests | confidence
MTG-20260906-072136 | 2026-09-06 |  | Prioritize SSO workstream | description='Security review is incomplete' impact='two-week schedule impact' owner='Security Team' status='Open' |  |  | Open |  | Customer provisioning Azure AD tenant (status: Open) |  |  |  |  | 0.6
MTG-20260906-072136 | 2026-09-06 |  | Prioritize SSO workstream | [5 empty] | Customer provisioning Azure AD tenant (status: Open) | task="Follow up with customer's IT team on Azure AD tenant" owner='David' due_date='2023-10-06' |  |  |  | 0.6
MTG-20260908-115926 | 2026-09-08 | Unknown Project | The team should verify the data integrity of the records to ensure there are no issues with specific records that might be causing the modify view functionality to fail.; The developer should check the console for any error messages that might indicate why the modify view is not working as expected.; The customer should try modifying different records to see if the issue is isolated to a specific record or if it's a broader problem with the functionality. | description='The modify view functionality might be failing due to issues with specific records.' impact='The customer might not be able to modify certain records, leading to incomplete or incorrect data.' owner='' status='Open' |  |  | Open | The customer is unable to see any changes in the console when attempting to modify a record.; The modify view functionality is not working as expected for some records. | The developer needs to check the console for any error messages.; The customer needs to try modifying different records to identify if the issue is isolated. |  |  |  | Verify and test the modify view functionality with different records to ensure it works as expected. | 0.7
MTG-20260908-115926 | 2026-09-08 | Unknown Project | The team should verify the data integrity of the records to ensure there are no issues with specific records that might be causing the modify view functionality to fail.; The developer should check the console for any error messages that might indicate why the modify view is not working as expected.; The customer should try modifying different records to see if the issue is isolated to a specific record or if it's a broader problem with the functionality. | description='There might be an error in the code that is not being caught by the console.' impact='The customer might experience unexpected behavior or errors when trying to modify records.' owner='' status='Open' |  |  | Open | The customer is unable to see any changes in the console when attempting to modify a record.; The modify view functionality is not working as expected for some records. | The developer needs to check the console for any error messages.; The customer needs to try modifying different records to identify if the issue is isolated. |  |  |  | Verify and test the modify view functionality with different records to ensure it works as expected. | 0.7